## Sheet1
No. | Meeting Date | Action | Assignee | Completed
1 | 1st August, 2017 | Ask Landscape Partnership to supply us with CAD maps of the files | Andrew | Completed
2 | 1st August, 2017 | Promote Local Green Space Designation and conservation area status for Stebbing Green through the NP. | NP | In progress
3 | 1st August, 2017 | Is it possible to include a "sign up" button for people to be included in our mailing list. | Bernard | Completed
4 | 1st August, 2017 | It was agreed that a regular email be sent out via email, Nextdoor and Facebook pointing to our website to look at NP updates and get them used to visiting the NP website. | Bernard | Completed
5 | 5th September, 2017 | Heritage Character assessment to be put on-line | Bernard | Completed
6 | 5th September, 2017 | Heritage Assessment summary to be produced for the benefit of residents who do not want to read the complete report | Robert | Completed
7 | 5th September, 2017 | Provide etc Gazebo for the village fete | Robert | Completed
8 | 8th September 2017 | Request a copy of the ECC forecast for school capacity to show what their forecast is for Stebbing school during the UDC plan period (should be on ECC website) | Andrew | Outstanding
9 | 8th September 2017 | Is the site for Stebbing Primary school constrained? (have been told they need to go up from 15 to 20 new entrants per year) | N/A | Close
10 | 8th September 2017 | Re-look at section SP3 in the UDC Reg 18 proposal to understand just how much housing Stebbing is expected to deliver in the UDC plan period (which started from 2016??) and confirm how many houses have already been built in the parish in this period, which would count towards the allocation. 44 houses in total across all Type A villages across full plan period, above existing commitments | N/A | Close (will include in no.12)
11 | 8th September 2017 | Create an annotated of the parish to show sites for CURRENT planning applications which have been approved or are pending, but building is not yet complete – including no. of houses for each site | Andrew | To be completed as we finish the plan.
12 | 8th September 2017 | Need to re-emphasise in all future comms that Stebbing NP cannot stop the WOB garden settlement development, but can help mitigate any impact on parish (this should reduce the risk of residents rejecting our NP at referendum inappropriately). | All | Completed
13 | 8th September 2017 | Obtain copy of Ben Smeedon report from April to use as evidence to our NP – the document references there should be a generous buffer zone between Stebbing Green and WOB development, but this was not included in Reg 18 proposal | Robert | Completed
14 | 8th September 2017 | Obtain copy of Chris Blandford’s report in relation to Braintree local plan proposal) and use as evidence in our NP – this document also references visual impact of WOB development on Stebbing Green. | Robert | Completed
15 | 8th September 2017 | Read up on Local Green Space Designation (LGSD) in the NPPF (paragraph/section 77). Identify potential open spaces within the parish which would meet the criteria and hence we could recommend are designated Local Green Space. | All | Completed
16 | 8th September 2017 | Obtain (via Rachel) a copy of the Locality template relating to Local Green Space Designation | Robert | Completed
17 | 8th September 2017 | Forward email information regarding wildlife and biodiversity sites from Margaret Rufus to Andrew (Robert) Add sites which are important in terms of wildlife and biodiversity to our NP constraints map. | Robert | Completed
18 | 8th September 2017 | All of the Steering Group (individually) need to draft a Vision statement along with a proposed list of objectives for our NP to compare, review and agree at the 19th September meeting – should be shared via email 17/18 Sept so people have chance to read before the meeting |  | Completed
19 | 19th September 2017 | Send Open Space society idiot's guide to green spaces to Robert | John
20 | 19th September 2017 | Continue to try to make contact with John Moore (Essex Wildlife Trust) for input to NP | Robert | Completed
21 | 19th September 2017 | Circulate updated Vision statement to group and Rachel Hogger with final amendments to be fed back and agreed by 30th Sept | Fran | Completed
22 | 3rd October | Review objective and chapter headings of other NP groups | Robert | Completed by Andrew.
23 | 31st October 2017 | Review local Green spaces list | All | Ongoing
24 | 31st October 2017 | Email list of local Green Spaces to all members | Robert | Complete
25 | 31st October 2017 | Add ancient / important hedges to plan | John | Ongoing
26 | 31st October 2017 | email all chapter documents to all | Robert | Complete
27 | 31st October 2017 | Email results from speed check to val | Greg | Complete
28 | 31st October 2017 | email community profile to Christina | Greg | Complete
29 | 31st October 2017 | Contact Rachel Hogger with a view to her attending another meeting | Robert | Ongoing
30 | 31st October 2017 | Check OFMH availability for Saturday 9th December | Greg | Complete
31 | 31st October 2017 | Change meeting date from 5th December to 28th November | Greg | Complete

## Sheet2
Proposals
Add Stebbing Green as an objective to be a Conservation Area and apply to UDC
Also include Stebbing Green, cricket field, Pulford field in list of sites to be designated as Local Green Space