## Sheet1
No. | Meeting Date | Action | Assignee | Completed
1 | 1st August, 2017 | Ask Landscape Partnership to supply us with CAD maps of the files | Andrew
2 | 1st August, 2017 | Promote Local Green Space Designation and conservation area status for Stebbing Green through the NP. | NP
3 | 1st August, 2017 | Is it possible to include a "sign up" button for people to be included in our mailing list. | Bernard
4 | 1st August, 2017 | It was agreed that a regular email be sent out via email, Nextdoor and Facebook pointing to our website to look at NP updates and get them used to visiting the NP website. | Bernard
5 | 1st August, 2017
6 | 5th September, 2017 | Heritage Character assessment to be put on-line | Bernard | Completed
7 | 5th September, 2017 | Heritage Assessment summary to be produced for the benefit of residents who do not want to read the complete report | Robert
8 | 5th September, 2017 | Provide etc Gazebo for the village fete | Robert | Completed
9 | 8th September 2017 | Request a copy of the ECC forecast for school capacity to show what their forecast is for Stebbing school during the UDC plan period (should be on ECC website) | Andrew
10 | 8th September 2017 | Is the site for Stebbing Primary school constrained? (have been told they need to go up from 15 to 20 new entrants per year) | N/A | Close
11 | 8th September 2017 | Re-look at section SP3 in the UDC Reg 18 proposal to understand just how much housing Stebbing is expected to deliver in the UDC plan period (which started from 2016??) and confirm how many houses have already been built in the parish in this period, which would count towards the allocation | N/A | Close (will include in no.12) | 44 houses in total across all Type A villages across full plan period, above existing commitments
12 | 8th September 2017 | Create an annotated of the parish to show sites for CURRENT planning applications which have been approved or are pending, but building is not yet complete – including no. of houses for each site | Andrew
13 | 8th September 2017 | Need to re-emphasise in all future comms that Stebbing NP cannot stop the WOB garden settlement development, but can help mitigate any impact on parish (this should reduce the risk of residents rejecting our NP at referendum inappropriately). | All | Ongoing
14 | 8th September 2017 | Obtain copy of Ben Smeedon report from April to use as evidence to our NP – the document references there should be a generous buffer zone between Stebbing Green and WOB development, but this was not included in Reg 18 proposal | Robert | Completed
15 | 8th September 2017 | Obtain copy of Chris Blandford’s report in relation to Braintree local plan proposal) and use as evidence in our NP – this document also references visual impact of WOB development on Stebbing Green. | Robert
16 | 8th September 2017 | Read up on Local Green Space Designation (LGSD) in the NPPF (paragraph/section 77). Identify potential open spaces within the parish which would meet the criteria and hence we could recommend are designated Local Green Space via our NP - Pulford Field, Alcott Field, Mill Lane cricket field, Stebbing Green, bottom area of church meadow (The Glebe?), "Kingdom's meadow", Bowling green, Bentmarshall's field behind Marshall's Piece, wildflower meadow by Stebbing Green, triangle opposite Marshall's Piece | Andrew | Completed
17 | 8th September 2017 | Obtain (via Rachel) a copy of the Locality template relating to Local Green Space Designation | Robert
18 | 8th September 2017 | Forward email information regarding wildlife and biodiversity sites from Margaret Rufus to Andrew (Robert) Add sites which are important in terms of wildlife and biodiversity to our NP constraints map. | Andrew
19 | 8th September 2017 | All of the Steering Group (individually) need to draft a Vision statement along with a proposed list of objectives for our NP to compare, review and agree at the 19th September meeting – should be shared via email 17/18 Sept so people have chance to read before the meeting
20 | 19th September 2017 | Send Open Space society idiot's guide to green spaces to Robert | John
21 | 19th September 2017 | Continue to try to make contact with John Moore (Essex Wildlife Trust) for input to NP | Robert
22 | 19th September 2017 | Circulate updated Vision statement to group and Rachel Hogger with final amendments to be fed back and agreed by 30th Sept | Fran
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244

## Sheet2
Proposals
Add Stebbing Green as an objective to be a Conservation Area and apply to UDC
Also include Stebbing Green, cricket field, Pulford field in list of sites to be designated as Local Green Space